## VE & ALT Log
Project Name:
VE, Alternates & Changes Log
Baseline Estimate:
Date of Issue:
Item # | Description | Status | Date of Status Change | Quantity | Unit Cost | Budget Amount | Approved Amount | Pending Amount | Add Backs
1 | Install a different type of siding on the west side of the building for the 3rd and 4th floors only |  |  | 1 | 62389 | 62389
2 | Construct five CMU trash enclosures |  |  | 5 | 16000 | 80000
3 | Install additional floor drains in eight dwelling units |  |  | 8 | 4281 | 34248
4 | Increase PSI of gypcrete to 3,500 |  |  | 1 | 9600 | 9600
5 | Remove window coverings for common spaces, community room, and offices |  |  | 10 | 193 | 1930
6 | Provide a doorbell for each dwelling unit |  |  | 45 | 25 | 1125
7 | Upgrade window warranty for storefront glass to 20-years |  |  | 1 | 4251 | 4251
8 | Increase the insulation for office walls |  |  | 1 | 8732 | 8732
9 | Upgrade countertops to Quartz |  |  | 1 | 48523 | 48523
10 | Change plumbing piping material to Cast-Iron in lieu of PVC |  |  | 1 | 94128 | 94128
[6 empty] | SUBTOTAL DIRECT COSTS: | 0 | 0 | 0
[5 empty] | General Conditions | 5% | 0
[5 empty] | Subtotal |  | 0
[5 empty] | Profit and Overhead | 4% | 0
[5 empty] | Subtotal |  | 0
[5 empty] | Insurance | 1% | 0
[5 empty] | P&P Bonds | 1% | 0
[5 empty] | OR Gross Receipt Tax | 0.4% | 0
[5 empty] | Subtotal |  | 0
[5 empty] | Total: |  | 0
[5 empty] | Baseline Estimate Grand Total: |  | 21587423
[5 empty] | Revised Budget: |  | 21587423
[5 empty] | Difference |  | 0

## Status Options
Add Alt
Pending
Approved
Rejected